## WorkPlan
*Project Name Here* Work Plan |  | *Work products listed are provided as an example of the types of work products SEMCOG is expecting.
Task / Sub Task | Products* | Grantee should customize this table according to their plan.
Task 1: Grant Administration and Close Out
a. Submit quarterly report to SEMCOG detailing project status. b. Document the project process with photographs of the site prior to, during, and after installation. | Quarterly Reports Before & After Photos
Task 2: Planning and Design
a. Perform hydrologic/hydraulic calcuations for design and metric reporting. b. Conduct topographic survey of existing condition and confirm existing infrastructure locations and conditions. c. Determine design layout of green infrastructure practices based on topographic survey and soil analysis. d. Develop engineering and landscaping plans. e. Submit engineering plans for SEMCOG and EPA review and approval prior to construction. Construction will not begin without approval. f. Finalize and distribute final construction and bid documents g. Finalize BMP O&M plan | Topographic Survey Soil Boring and Infiltration Test Report Construction Documents (i.e. engineering plans and specifications) including hydrologic design details, metrics, and landscape plans Final Contract and Bid Documents O&M Plan
Task 3: Construction and Implementation
a. Obtain all required local and state permits for project activities. All permits from external agencies must be secured prior to construction. SHPO coordination should be initated early to accomodate its typical review timeline. b. Obtain quotes and award contracts following EPA procurement guidelines. c. Installation of green infrastructure project components, including signage. d. Update project metric calculations to reflect the as-built condition. | Completed Permit Application Package Quotes and Bid Packages from Contractors As‐Built Construction Drawings
Task 4: Stakeholder Engagement & Educational Outreach
a. Community and stakeholder engagement. | Summary of Community and Stakeholder Engagement Efforts (as part of quarterly reports)

## WorkPlanTimeTable
Project Title:
| 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030
Task / SubTask | Q1: Jan. - March | Q2: April - June | Q3: July - Sept | Q4: Oct - Dec. | Q5: Jan - March | Q6: April - June | Q7: July - September | Q8: Oct. - Dec. | Q9: Jan. - March | Q10: April - June | Q7: July - Sept | Q8: Oct. - Dec. | Q5: Jan - March | Q6: April - June
Task 1. Grant Administration and Close Out
1a. - Quarterly Reports
1b. -
Task 2. Planning and Design
2a. -
2b. -
2c. -
2d. -
2e. -
2f. -
2g. -
Task 3. Construction and Implementation
3a. -
3b. -
3c. -
3d. -
Task 4. Stakeholder Engagement & Educational Outreach
4a. -
Note on B5: Don Carpenter: Applicant should put subtask information (aka "Products) from Work Plan on each row and complete the Timeframe accordingly.